## BEACH CLUB
CODE | AREA | PROGRESS | KETERANGAN | PIC
MW.BC1-01 | CONCIERGE | Cutting marble done - finishing & bullnose belum. Posisi fix id belum fix | Menunggu tim ME & operator berdiskusi baru bisa di fix kan posisi nya. Setelah fix baru bisa finishing bullnose | ME & OPERATOR
MW.BC1-02 | RECEPTIONIST | Cutting marble done - finishing & bullnose belum. Posisi fix id belum fix | Menunggu tim ME & operator berdiskusi baru bisa di fix kan posisi nya. Setelah fix baru bisa finishing bullnose | ME & OPERATOR
MW.BC1-03A | CABANA A | Perbaikan rangka patah saat delivery - on progress | Pekerjaan ceiling di atas cabana harus sudah selesai finishing | CK | BYO
MW.BC1-03B | CABANA B | Perbaikan rangka patah saat delivery - on progress | Pekerjaan ceiling di atas cabana harus sudah selesai finishing | CK | BYO
MW.BC1-03C | CABANA C | Perbaikan rangka patah saat delivery - on progress | Pekerjaan ceiling di atas cabana harus sudah selesai finishing | CK | BYO
MW.BC1-04A | TOILET CUBICLE A | Installed | Belum finishing | CK | BURHAN
MW.BC1-04B | TOILET CUBICLE B | Installed | Belum finishing | CK | BURHAN
MW.BC1-04C | TOILET CUBICLE C | Installed | Belum finishing | CK | BURHAN
MW.BC1-05A | SINK VANITY A | Cutting marble on progress - Base kaki kayu belum on-site | Pengiriman 15/07/26 | CK | TOHA
MW.BC1-05B | SINK VANITY B | Cutting marble on progress - Base kaki kayu belum on-site | Pengiriman 15/07/26 | CK | TOHA
MW.BC1-06 | CASHIER STATION | Barang belum on-site | Pengiriman 15/07/26 | CK | ANDIK
MW.BC1-07A | BUFFET ISLAND | Cutting marble done - finishing & bullnose belum. Menunggu kitchen equipment | Kitchen equipment (KANWAH) belum on-site | KANWAH, CK | HADI, TOHA
MW.BC1-07B | PIZZA COUNTER | Cutting marble done - finishing & bullnose belum. Menunggu kitchen equipment | Kitchen equipment (KANWAH) belum on-site | KANWAH, CK | HADI, TOHA
MW.BC1-08 | PIZZA OVEN (MOSAIC) | Menunggu proses purchasing | Material mosaic belum on-site | CK | CK PUSAT
MW.BC1-10 | DESSERT COUNTER | Cutting marble done - finishing & bullnose belum. Menunggu kitchen equipment | Kitchen equipment (KANWAH) belum on-site | KANWAH, CK | HADI, TOHA
MW.BC1-12A | BAR | Cutting marble done - finishing & bullnose belum. Menunggu kitchen equipment | Kitchen equipment (KANWAH) belum on-site | KANWAH, CK | HADI, TOHA
MW.BC1-12B | BAR SHELVING | Menunggu pemasangan panel rope | Ada masalah dengan bentuk panel rope. Solusi? | CK | BYO & HADI
MW.BC1-13A | BAR HANGING SHELVING | Installed
MW.BC1-13B | BUFFET ISLAND SHELVING | Installed
MW.BC1-14A | SINK VANITY MIRROR A | On-site | Menunggu panel C05 terpasang & finished | CK | BURHAN
MW.BC1-14B | SINK VANITY MIRROR B | On-site | Menunggu panel C05 terpasang & finished | CK | BURHAN
MW.BC1-15 | URINOIR PARTITION | On-site | Menunggu mosaic TL06 selesai terpasang | CK | TOHA, BURHAN
MW.BC1-16 | VANITY MIRROR | Belum produksi | Kendala? | CK | CK PUSAT
MW.BC1-17 | ADA TOILET MIRROR | On-site | Menunggu panel C05 terpasang | CK | BURHAN
D.BC-1 | DOOR TO BOH | Installed & Finished | Kurang Door Closer | CK | CK PUSAT
D.BC-2 | DOOR TO JANITOR | Installed | Belum finishing | CK | HENRI CAT
D.BC-3 | DOOR TO PUBLIC TOILET | Installed | Belum finishing | CK | ANDIK
D.BC-3A | DOOR TO ADA TOILET | On-site, belum terpasang | Ada balok di dinding toilet ADA. Solusi? | CK, MK, DOMI | ANDIK
D.BC-4 | DOOR TO CUBICLE TOILET | Installed | Handle & accessories belum terpasang | CK | BURHAN, CK PUSAT
D.BC-5 | DOOR TO BACK KITCHEN | On-site, baru terpasang kusen | Hardware floor hinge baru ada 1 set. Cek Surat Jalan | CK | ANDIK
GW.BC-1 | GATE TO CORRIDOR TOILET | Installed | Perlu revisi lebar gawangan & belum di finish | CK | BURHAN
GW.BC-2 | GATE TO CORRIDOR TOILET MALE | Installed | Perlu revisi lebar gawangan & belum di finish | CK | BURHAN
GW.BC-3 | GATE TO CORRIDOR TOILET FEMALE | Installed | Perlu revisi lebar gawangan & belum di finish | CK | BURHAN
GW.BC-4 | OPEN KITCHEN ARCHWAY | Installed | Revisi bentuk untuk menutup beam & proses finishing SP-04 | CK | AGA
GW.BC-5 | OPEN KITCHEN ARCHWAY | Installed | Revisi bentuk untuk menutup beam & proses finishing SP-04 | CK | AGA
GW.BC-6 | GATE TO BUFFET AREA | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-7 | OPEN KITCHEN ARCHWAY | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-7A | GATE TO ALL ADD | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-8 | GATE TO BAR AREA / REAR FAÇADE | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-8A | GATE TO STAIRCASE / REAR FAÇADE | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-8B | GATE TO ADD | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-9 | GATE TO ADD | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-10 | GATE TO BUFFET ISLAND | Installed | Proses finishing SP-04 | CK | HENRI CAT
GW.BC-11 | GATE TO BUFFET ISLAND | Installed | Proses finishing SP-04 | CK | HENRI CAT
C-05 | PANEL TRIBAL | Male Toilet | Panel proses pemasangan & belum di-finish | CK | BURHAN
|  | Female Toilet | Panel sudah terpasang & belum di-finish | CK | BURHAN
|  | ADA - belum terpasang & belum finishing | Panel belum terpasang & belum di-finish | CK | BURHAN
SP-04 WALL | TEXTURE PAINT | Reception | Dinding belum teraci | NRC
|  | Kolom | Proses perbaikan | CK | HENRI CAT
|  | Penebalan dinding kitchen | Belum mulai - penambahan plinth HT-04 | CK | HENRI CAT, HENDIKA
|  | Landing toilet Beach Club | Plinth HT-04 belum terpasang - dinding belum perapian by NRC | CK, NRC | HENRI CAT
ST-06B | ROUGH STONE TEXTURE | Semua area | Perbaikan pertemuan dengan plinth HT-04 | CK | ROBIN
TL-06 | SOLO DESIGN MOSAIC | Female Toilet | Masih kurang 1 cubicle toilet | CK | TOHA
|  | Male Toilet | Penambahan 1 baris mosaic | CK | TOHA
SP-04 CEILING | TEXTURE PAINT | On progress | Kurang manpower | CK | HENRI CAT
C-08 | PHOMI ROPE | Installed | Belum finish - masih di review DOMI untuk warna nya | DOMI, CK | HENRI CAT
GRC PROFILE 1 |  |  | Proses finishing | CK | AGA, HENRI CAT
GRC PROFILE 2 |  |  | Belum terpasang | CK | AGA, HENRI CAT
GRC PROFILE 3 | BAR AREA | Installed | Proses finishing | CK | AGA, HENRI CAT
GRC PROFILE 4 | DINING AREA | Installed | Proses finishing | CK | AGA, HENRI CAT
OVAL STAIRS | STAIRCASE RAILING | Proses pembentukan kompon | Belum finishing SP-04 | CK | HENRY GYPSUM
| HANDRAIL | Belum on-site | Pengiriman 15/07/26 | CK | ANDIK
| FLOORING HT-04 | Proses pemasangan | Perapian dan finishing | CK | HENDIKA
| FIN. BAWAH TANGGA | Proses kompon | Belum finishing SP-04 | CK | HENRY GYPSUM
ROUND STAIRS | STAIRCASE RAILING | Proses pemasangan backing plywood | Belum pembentukan kompon & finishing SP-04 | CK | HENRY GYPSUM
| HANDRAIL | Belum on-site | Pengiriman 15/07/26 | CK | ANDIK
| FLOORING WPC-02 (WD-08) | Material on-site | Belum terpasang & belum finishing | CK | HENDIKA
| FIN. BAWAH TANGGA | Proses kompon | Belum finishing SP-04 | CK | HENRY GYPSUM

## SPA LOBBY
CODE | AREA | PROGRESS | KETERANGAN | PIC
MW.SL-01 | RECEPTION TABLE | Barang belum on-site. Top Table belum produksi. ST-06A belum produksi. | Pengiriman 15/07/26 | CK | ANDIK, ROBIN, TOHA
MW.SL-02 | RECEPTION PARTITION | Barang belum on-site. | Pengiriman 15/07/26 | CK | BURHAN
MW.SL-03 | DISPLAY SHELVES | Barang on-site | Belum terpasang, perlu manpower tambahan | CK | BURHAN
MW.SL-05 | PARTITION SCREEN A | Barang on-site | Belum terpasang, lantai perlu di finish | NRC | BURHAN
MW.SL-06 | PARTITION SCREEN B | Barang on-site | Belum terpasang, lantai perlu di finish | NRC | BURHAN
MW.SL-07 | PARTITION SCREEN C | Barang on-site | Belum terpasang, lantai perlu di finish | NRC | BURHAN
MW.SL-11 | VANITY MALE FEMALE | Installed | Belum finishing, top table on progress | CK | ROBIN, TOHA
MW.SL-12 | LOCKER & TOWEL STATION FEMALE | Installed
MW.SL-13 | LOCKER MALE | Installed
MW.SL-14 | DRY VANITY (FEMALE) | Installed | Belum finishing, top table on progress | CK | ROBIN, TOHA
MW.SL-15 | TOWEL STATION (MALE) | Installed | Top table on progress | CK | TOHA
MW.SL-16 | STAFF PANTRY | Installed | Top table on progress | CK | TOHA
MW.SL-17 | TATAMI SEATING | Barang on-site | Belum terpasang, lantai perlu di finish | NRC | HADI
MW.SL-18 | VANITY (STAFF TOILET) | Installed | Top table on progress | CK | TOHA
MW.SL-19 | AC COVER | Barang sudah sampai mana? | Belum terpasang, perlu manpower tambahan | CK | HADI
DSL-1 | ENTRANCE DOOR | Barang on-site | Belum terpasang, perlu manpower tambahan | CK | CK PUSAT
DSL-2 | DOOR TO JANITOR, CHANGING ROOM | Installed | Belum finishing | CK | HENRI CAT
DSL-2B | DOOR TO MEP, LINEN | Pemasangan on-progress | Belum terpasang & belum finishing | CK | ANDIK
DSL-2C | DOOR TO JANITOR BOH | On-site, belum terpasang | Belum terpasang, perlu manpower tambahan | CK, MK, DOMI | ANDIK
DSL-3 | GLASS DOOR TO LOUNGE | Barang on-site | Belum terpasang - ukurang openingan salah, tidak sesuai Forcon interior | CK | MK, NRC
DSL-6 | DOOR TO SHOWER/TOILET | Pemasangan on-progress | Belum terpasang & belum finishing | CK | ANDIK
DSL-7 | DOOR TO TOILET BOH | Pemasangan on-progress | Belum terpasang & belum finishing | CK | CK PUSAT
DSL-8 | DOOR TO STAFF ROOM | Pemasangan on-progress | Belum terpasang & belum finishing | CK | HENRI CAT
DSL-9 | DOOR TO BOH AREA | On-site, belum terpasang | Belum terpasang, perlu manpower tambahan | CK | ANDIK
DSL-11 | GLASS DOOR TO SPA MANAGER | Masih produksi | Belum terpasang | CK, MK, DOMI | ANDIK
WD-06 | PANEL CUBICLE KAMAR MANDI |  |  | CK | ANDIK
SP-01 | WALL AREA SPA |  |  | CK | BU DEBY
| CEILING AREA SPA |  |  | CK | BU DEBY
SP-02 | AREA SPA |  |  | CK | BU DEBY
PT-01 | WALL BOH |  |  | CK | HENRI CAT
| CEILING AREA SPA |  |  | CK | BU DEBY

## SPA TENT
CODE | AREA | PROGRESS | KETERANGAN | PIC
MW.ST-01 | CUSTOM VANITY (SINGLE SPA 1) |  |  | CK
MW.ST-02 | CUSTOM VANITY (SINGLE SPA 2) |  |  | CK
MW.ST-05 | AC COVER |  |  | CK
MR.ST-1A | VANITY MIRROR (SINGLE SPA 1) |  |  | CK
MR.SL-2A | VANITY MIRROR (SINGLE SPA 2) |  |  | CK
MR.ST-1B | VANITY MIRROR (COUPLE SPA 1) |  |  | CK
MR.SL-2B | VANITY MIRROR (COUPLE SPA 2) |  |  | CK
MW.ST-06 | EXHAUST COVER | Barang belum produksi |  | CK
H.ST-01 | HANGER | Barang belum produksi |  | CK
D.ST-01 | FRONT DOOR | Barang on-site |  | CK | ANDIK
D.ST-04 | BATHROOM SLIDING DOOR (COUPLE SPA) | Barang on-site |  | CK | ANDIK
D.ST-05 | BATHROOM DOOR (COUPLE SPA) |  |  | CK | ANDIK
WD-01 | CEILING SPA TENT | Barang belum produksi |  | CK | CK PUSAT
SP-01 | WALL AREA SPA |  |  | CK | BU DEBY
SP-01B | WALL AREA SPA BASAH |  |  | CK | HENRI CAT
SP-02 | AREA SPA |  |  | CK | BU DEBY

## Sheet1
Item belum sampai di lokasi
BASE MW.BC1-5A | 15 JULI 2026
BASE MW.BC1-5B | 15 JULI 2026
MW.BC1-6 | 15 JULI 2026
MW.BC1-16